## Assignments
Frontend Major Project | Due Date: Nov 27
Bibishan Pandey (C0914078) Channpreet Singh (C0904176) Kabita Shrestha (C0909917) Rupesh Shrestha (C0908441) | Terrace Fitness Club
Week 9 (Done)
Start date | Student | Assignment | Status
2023-11-07 | Bibishan Pandey | Research about the fitness club pages and page contents | Done
2023-11-07 | Channpreet Singh | Research about the CSS elements to be used like navigation and color schemes | Done
2023-11-07 | Kabita Shrestha | Research about the wireframes for the pages | Done
2023-11-07 | Rupesh Shrestha | Research about the targert audience and graphics like logo, banner | Done
Week 10 (Done)
Start date | Student | Assignment | Status
2023-11-14 | Bibishan Pandey | - Wireframing Home page for mobile, tablet, and desktop view - Draw sitemap for the site | Done
2023-11-14 | Channpreet Singh | - Worked on Products page for mobile, tablet, and desktop view | Done
2023-11-14 | Kabita Shrestha | - Working on Contact page and search for mobile, tablet and desktop view | Done
2023-11-14 | Rupesh Shrestha | - Design responsive about us page | Done
Week 11 (Done)
Start date | Student | Assignment | Status
2023-11-21 | Bibishan Pandey | - Design and implement responsive home page | Done
2023-11-21 | Channpreet Singh | - Working on CSS styles for Products page (Mobile first approach) | Done
2023-11-21 | Kabita Shrestha | - Working on HTML & CSS styles for Contact page (Mobile first approach) | Done
2023-11-21 | Rupesh Shrestha | - working on About Us page and checking if the HTML and CSS requirements meet | Done
Week 12 (Done)
Start date | Student | Assignment | Status
2023-11-28 | Bibishan Pandey | - Collaborating and synchronizing the website | Done
2023-11-28 | Channpreet Singh | - Collaborating and synchronizing the website | Done
2023-11-28 | Kabita Shrestha | - Collaborating and synchronizing the website | Done
2023-11-28 | Rupesh Shrestha | - Collaborating and synchronizing the website | Done

## Students
Students
Bibishan Pandey
Channpreet Singh
Kabita Shrestha
Rupesh Shrestha